## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Project continuing to run well. Web Application is complete with all fully functioning pages. Desktop application is running slightly behind. Will need another week to work on it. | 
Status as of | 3-Apr-19
Business Lead | Jim Worth
Project Manager | Tyler Carrier
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 80% | 3/24 | 4/10
Testing |  | 0% | 4/6 | 
Remediation |  | 0% | 4/21 | 
Training and Doc |  | 0% | 5/8 | 
Deployment |  | 0% | 4/22 | 
Hyper Care Support |  | 0% | 4/30 | 
Ongoing Support |  | 0% | n/a | 
# | Key Accomplishments (Current Period)
1 | Completed all pages in web application (finished home page, created edit page)
2 | Desktop Application frames (Login and Search Frame) have been created without functionality
3 | 
# | Upcoming Activities (Next Period through (04/10/2019)
1 | Create Faculty Registration Page
2 | Reinstate login functionality (database connection)
3 | Populate search table with database information
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Project running slightly behind. Will need another week. | med | med | Complete Desktop Application | n/a | high | 4/10
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
CairnU Alumni Search Tool