## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Difficulty with search results when switching table models. Will get it fixed. | 
Status as of | 1-May-19
Business Lead | Jim Worth
Project Manager | Tyler Carrier
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 95% | 3/24 | 
Testing |  | 90% | 4/18 | 
Remediation |  | 90% | 4/21 | 
Training and Doc |  | 100% | 5/8 | 
Deployment |  | 0% | 4/22 | 
Hyper Care Support |  | 0% | 4/30 | 
Ongoing Support |  | 0% | n/a | 
# | Key Accomplishments (Current Period)
1 | Made progress towards search functionality
2 | Created user training documentation
3 | 
# | Upcoming Activities (Next Period through (05/1/2019)
1 | Fix search table bugs
2 | Fix edit page bug
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Difficulty when switching table models | High | High | Fix bug | n/a | high | 5/8
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Difficulty when switching table models | High | High | Fix bug | n/a | High | 5/8
CairnU Alumni Search Tool