## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Project running smoothly. Desktop Application is still being worked on. | 
Status as of | 10-Apr-19
Business Lead | Jim Worth
Project Manager | Tyler Carrier
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 85% | 3/24 | 4/14
Testing |  | 20% | 4/18 | 
Remediation |  | 0% | 4/21 | 
Training and Doc |  | 0% | 5/8 | 
Deployment |  | 0% | 4/22 | 
Hyper Care Support |  | 0% | 4/30 | 
Ongoing Support |  | 0% | n/a | 
# | Key Accomplishments (Current Period)
1 | Created Registration Page along with database connection for desktop app
2 | Created Home Frame with displayable search bar and search table. Hardcoded search results are apparent.
3 | Login functionality has been reinstated
# | Upcoming Activities (Next Period through (04/10/2019)
1 | Fix search table bug when changing size
2 | Populate search table with database results
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Login bug with password hashing | med | high | Fix bug | n/a | high | 4/13
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Desktop application needs a few more days | med | med | Complete by 4/14 | n/a | high | 4/14
CairnU Alumni Search Tool