## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Project is running smoothly. Have been having hard time with switch from Eclipse to NetBeans. I have been putting my main focus on the web application. Once that is completed, I will move to finishing desktop application afterwards. | 
Status as of | 20-Mar-19
Business Lead | Jim Worth
Project Manager | Tyler Carrier
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 55% | 3/24 | 
Testing |  | 0% | 4/6 | 
Remediation |  | 0% | 4/21 | 
Training and Doc |  | 0% | 5/8 | 
Deployment |  | 0% | 4/22 | 
Hyper Care Support |  | 0% | 4/30 | 
Ongoing Support |  | 0% | n/a | 
# | Key Accomplishments (Current Period)
1 | Created basic pages for all pages on web application
2 | Successfully created login/registry pages with database cooperation
3 | Completed the following pages: Contact Page, Register Page, Login Page, Successful Submission Page
# | Upcoming Activities (Next Period through (03/13/2019)
1 | Create basic homepage will include basic information (change)
2 | Populate profile page based on php session
3 | Finalize minor details (smoothing, format, and prepared statements for queries)
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
CairnU Alumni Search Tool