## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Project is running smoothly. Web Application is nearly finished. | 
Status as of | 27-Mar-19
Business Lead | Jim Worth
Project Manager | Tyler Carrier
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 70% | 3/24 | 
Testing |  | 0% | 4/6 | 
Remediation |  | 0% | 4/21 | 
Training and Doc |  | 0% | 5/8 | 
Deployment |  | 0% | 4/22 | 
Hyper Care Support |  | 0% | 4/30 | 
Ongoing Support |  | 0% | n/a | 
# | Key Accomplishments (Current Period)
1 | Account Page, Contact Page, and Give Page are now completed
2 | Profile Page is successfully populated with database info from user session
3 | Website layout is mostly finished
# | Upcoming Activities (Next Period through (04/3/2019)
1 | Finishing touches on web app (populate home page, add logout functionality, smooth layout of profile information
2 | Finish creating desktop application
3 | 
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
CairnU Alumni Search Tool