## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Project is running smoothly. There was a firewall error when connection to database. I informed Professor Sabal, and permissions were adjusted. | 
Status as of | 27-Feb-19
Business Lead | Jim Worth
Project Manager | Tyler Carrier
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 8% | 3/24 | 
Testing |  | 0% | 4/6 | 
Remediation |  | 0% | 4/21 | 
Training and Doc |  | 0% | 5/8 | 
Deployment |  | 0% | 4/22 | 
Hyper Care Support |  | 0% | 4/30 | 
Ongoing Support |  | 0% | n/a | 
# | Key Accomplishments (Current Period)
1 | Created Login Page
2 | Created Login to Home Page Functionality
3 | Established database connection
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Create user authentication with prepared statements on Login Page
2 | Begin creating structure for Home Page
3 | Establish database connection on Home Page
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Could be further permissions errors when connecting to database | Hi | Hi | Stay in contact with Professor Sabal and tech services to ensure permission to database | Tyler Carrier | Med | 02/27
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Permissions error when connecting to database | Hi | Hi | Spoke with Professor Sabal. He contacted tech services, and they were able to adjust the permissions | Tyler Carrier | Hi | 02/25
CairnU Alumni Search Tool